## Sheet1
Level | Module | Section | Topic | Subtopic | UID | Time | Planned Dates | Actual Dates | Status | Trainer
Foundation | Introduction | Program Overview | Program Details | Course Overview |  | 10 | 2025-04-08 | 2025-04-08 | Completed | Nagaraju
Foundation | Introduction | Overview of Fullstack Development | Definition of fullstack development | Introduction to Fullstack Development |  | 15 | 2025-04-08 | 2025-04-08 | Completed | Nagaraju
Foundation | Introduction | Overview of Fullstack Development | Role of a fullstack developer | History and Evolution |  | 10 | 2025-04-08 | 2025-04-08 | Completed | Nagaraju
Foundation | Introduction | Overview of Fullstack Development | Fullstack development lifecycle | Key Concepts and Terminology |  | 15 | 2025-04-08 | 2025-04-08 | Completed | Nagaraju
Foundation | Introduction | Overview of Fullstack Development | Current trends in fullstack development | Comparing Fullstack with Specialized Roles |  | 15 | 2025-04-08 | 2025-04-08 | Completed | Nagaraju
Foundation | Introduction | Frontend vs Backend | Frontend technologies overview (HTML, CSS, JavaScript) | Diff btw webtech... |  | 10 | 2025-04-08 | 2025-04-08 | Completed | Nagaraju
Foundation | Introduction | Frontend vs Backend | Backend technologies overview | mern/django/java |  | 15 | 2025-04-08 | 2025-04-08 | Completed | Nagaraju
Foundation | Introduction | Frontend vs Backend | Difference between frontend and backend development | routes to backend api through frontend |  | 20 | 2025-04-08 | 2025-04-08 | Completed | Nagaraju
Foundation | Introduction | Frontend vs Backend | Fullstack integration concepts | Fullstack integration concepts |  | 10 | 2025-04-08 | 2025-04-08 | Completed | Nagaraju
Foundation | Introduction | Development Environment Setup | Installing Python and necessary tools | Installing Python and necessary tools |  | 20 | 2025-05-08 | 2025-05-08 | Completed | Nagaraju
Foundation | Introduction | Development Environment Setup | Setting up a code editor (e.g., VS Code) | Setting up a code editor (e.g., VS Code) |  | 20 | 2025-05-08 | 2025-05-08 | Completed | Nagaraju
Foundation | Introduction | Development Environment Setup | Introduction to virtual environments | Introduction to virtual environments |  | 20 | 2025-05-08 | 2025-05-08 | Completed | Nagaraju
Foundation | Introduction | Development Environment Setup | Basic command line usage for developers | Basic command line usage for developers |  | 20 | 2025-05-08 | 2025-05-08 | Completed | Nagaraju
Foundation | Frontend Foundations | Web Development Basics | Internet and web architecture | Internet and web architecture |  | 15 | 2025-05-08 | 2025-05-08 | Completed | Nagaraju
Foundation | Frontend Foundations | Web Development Basics | Client-server model | Client-server model |  | 15 | 2025-05-08 | 2025-05-08 | Completed | Nagaraju
Foundation | Frontend Foundations | Web Development Basics | HTTP protocol basics | HTTP protocol basics |  | 20 | 2025-06-08 | 2025-06-08 | Completed | Nagaraju
Foundation | Frontend Foundations | Web Development Basics | Web browsers and how they work | Web browsers and how they work |  | 15 | 2025-06-08 | 2025-06-08 | Completed | Nagaraju
Foundation | Frontend Foundations | HTML5 Fundamentals | HTML structure and syntax | HTML structure and history |  | 25 | 2025-06-08 | 2025-06-08 | Completed | Nagaraju
Foundation | Frontend Foundations | HTML5 Fundamentals | HTML elements tags | HTML elements basics |  | 30 | 2025-06-08 | 2025-06-08 | Completed | Nagaraju
Foundation | Frontend Foundations | HTML5 Fundamentals | HTML structure and syntax | Basics tags <P> / > <h1> |  | 30 | 2025-06-08 | 2025-06-08 | Completed | Nagaraju
Foundation | Frontend Foundations | HTML5 Fundamentals | Common HTML tags and elements | Common HTML tags and elements |  | 30 | 2025-07-08 | 2025-07-08 | Completed | Nagaraju
Foundation | Frontend Foundations | HTML5 Fundamentals | Html Table tags | Tables tags from its bases |  | 30 | 2025-07-08 | 2025-07-08 | Completed | Nagaraju
Foundation | Frontend Foundations | HTML5 Fundamentals | Common HTML tags and elements | list types and order and unorder list and description list |  | 35 | 2025-07-08 | 2025-07-08 | Completed | Nagaraju
Foundation | Frontend Foundations | HTML5 Fundamentals | Semantic HTML | Theory about semantic tags |  | 35 | 2025-07-08 | 2025-07-08 | Completed | Nagaraju
Foundation | Frontend Foundations | HTML5 Fundamentals | footer tags vs navbar | Nav tags footer tags seprated html5 tags |  | 35 | 2025-07-08 | 2025-07-08 | Completed | Nagaraju
Foundation | Frontend Foundations | HTML5 Fundamentals | Typed of inputs | brief about Forms and input types |  | 35
Foundation | Frontend Foundations | HTML5 Fundamentals | Forms and input types | Forms and input types |  | 35
Foundation | Frontend Foundations | HTML5 Fundamentals | HTML5 features and APIs | HTML5 features and APIs in canvas history |  | 30
Foundation | Frontend Foundations | HTML5 Fundamentals | Multimedia elements (audio, video) | Multimedia elements (audio, video) and its use cases |  | 35
Foundation | Frontend Foundations | HTML5 Fundamentals | HTML5 APIs (Canvas, Geolocation, Web Storage) | HTML5 APIs (Canvas, Geolocation, Web Storage) |  | 35
Foundation | Frontend Foundations | HTML5 Fundamentals | Iframe tags in html | HTML LINKEDIn tags and iframetags for Youtube |  | 35
Foundation | Frontend Foundations | Html5 project wiki | Html ending project | Project hands on |  | 50
Foundation | Frontend Foundations | CSS3 | CSS Syntax, selectors | Types of selectors in css compare in css 1 ,2,3 |  | 40
Foundation | Frontend Foundations | CSS3 | id selector | id attribute selector |  | 40
Foundation | Frontend Foundations | CSS3 | class selector and universal selectors | id attribute selector |  | 40
Foundation | Frontend Foundations | CSS3 | Box model and layout | Real life Box model |  | 40
Foundation | Frontend Foundations | CSS3 | Button using boxmodel | Margin vs padding diff |  | 40
Foundation | Frontend Foundations | CSS3 | types inside boxmodel | Border vs content |  | 40
Foundation | Frontend Foundations | CSS3 | PSUEDO ELEMENTS | types of psuedo elements all types |  | 60
Foundation | Frontend Foundations | CSS3 | PSUEDO CLASSES | TYPES OF psuedo classes |  | 40
Foundation | Frontend Foundations | CSS3 | Using Psuedo hover | hover,link and active tags examples |  | 35
Foundation | Frontend Foundations | CSS3 | Making amazon button | hover example code practice |  | 20
Foundation | Frontend Foundations | CSS3 | Css flot properties | css float task with explaination |  | 35
Foundation | Frontend Foundations | CSS3 | Css positions | css positions |  | 30
Foundation | Frontend Foundations | CSS3 | real world static pages | static vs relative |  | 30
Foundation | Frontend Foundations | CSS3 | relative points vs absolute | using of relative and absolute realtime practice |  | 40
Foundation | Frontend Foundations | CSS3 | Fixed position | fixed example |  | 40
Foundation | Frontend Foundations | CSS3 | sticky position vs Fixed | sticky navbar amazon clone |  | 40
Foundation | Frontend Foundations | CSS3 | Css z-index | zindex example |  | 30
Foundation | Frontend Foundations | CSS3 | css overflow | Overflow examples in any conditions |  | 35
Foundation | Frontend Foundations | CSS3 | real world usecases of overflow | overflow examples terms and conditions |  | 35
Foundation | Frontend Foundations | CSS3 | css display properties | display inline and block level elements |  | 35
Foundation | Frontend Foundations | CSS3 | Responsive design and media queries | media queries |  | 30
Foundation | Frontend Foundations | CSS3 | CSS animations and transitions | keyframes in animations |  | 25
Foundation | Frontend Foundations | Bootstrap | Bootstrap Containers and Grid Systems | Grids and flex |  | 40
Foundation | Frontend Foundations | Bootstrap | Bootstrap Tables and Images | images and md values |  | 30
Foundation | Frontend Foundations | Bootstrap | Bootstrap Progress bar, Nav bar and pagination | components |  | 50
Foundation | Frontend Foundations | Bootstrap | Bootstrap form layouts and Carousel | layouts |  | 50
Foundation | Frontend Foundations | Bootstrap | Bootstrap Project - Themes Intro | mdb intro and use cases |  | 40
Foundation | Frontend Foundations | Bootstrap | single page project combinantion html css | Project hands on |  | 70
Foundation | Frontend Foundations | Javascript Fundamentals | Livescript | Introduction javascript |  | 30
Foundation | Frontend Foundations | Javascript Fundamentals | Modules diff btw java and javasvript | java vs javascript |  | 30
Foundation | Frontend Foundations | Javascript Fundamentals | JavaScript syntax | Introduction javascript |  | 30
Foundation | Frontend Foundations | Javascript Fundamentals | live script | Java vs live script |  | 40
Foundation | Frontend Foundations | Javascript Fundamentals | JavaScript syntax | compiler vs interpreter in usecases |  | 30
Foundation | Frontend Foundations | Javascript Fundamentals | Dailog boxes | alert in real world cases |  | 30
Foundation | Frontend Foundations | Javascript Fundamentals | simple alerts in website | alert vs prompt |  | 30
Foundation | Frontend Foundations | Javascript Fundamentals | Data Types | types of data types |  | 40
Foundation | Frontend Foundations | Javascript Fundamentals | primitve vs non primitive | primitve data types, non primitive |  | 40
Foundation | Frontend Foundations | Javascript Fundamentals | variables | types variables in js |  | 40
Foundation | Frontend Foundations | Javascript Fundamentals | es6 variables | let vs var vs const scope variables |  | 30
Foundation | Frontend Foundations | Javascript Fundamentals | Operators | types of operators in js |  | 40
Foundation | Frontend Foundations | Javascript Fundamentals | and control structures | statements in js |  | 30
Foundation | Frontend Foundations | Javascript Fundamentals | Functions and scope | Function types in es concepts |  | 35
Foundation | Frontend Foundations | Javascript Fundamentals | arrow vs old age functions | types of functions |  | 35
Foundation | Frontend Foundations | Javascript Fundamentals | DOM manipulation | dom types elements by id and query selectors |  | 55
Foundation | Frontend Foundations | Javascript Fundamentals | dom text content methods | textcontent vs innerhtml |  | 40
Foundation | Frontend Foundations | Javascript Fundamentals | Event Handling,Error handling and debugging | types of events onclick events ...etc |  | 50
Foundation | Frontend Foundations | Javascript Fundamentals | event listeners in js | types of event listeners |  | 50
Foundation | Frontend Foundations | Javascript Fundamentals | JavaScript ES6+ features (let, const, arrow functions) | live vs ecma script |  | 40
Foundation | Frontend Foundations | Javascript Fundamentals | ECMA | what is es6 and ecma models |  | 40
Foundation | Frontend Foundations | Modern JavaScript and ES6+ | Arrow functions | types of functions |  | 30
Foundation | Frontend Foundations | Modern JavaScript and ES6+ | Destructuring and spread operator | arrays using spread operators |  | 30
Foundation | Frontend Foundations | Modern JavaScript and ES6+ | Promises and async/await | promise events |  | 40
Foundation | Frontend Foundations | Modern JavaScript and ES6+ | callback hell | most interviewed q/a callback hell |  | 40
Foundation | Frontend Foundations | Modern JavaScript and ES6+ | Modules and import/export | Modules and import/export |  | 40
Foundation | Frontend Foundations | Modern JavaScript and ES6+ | Template literals | Template literals |  | 30
Foundation | Frontend Foundations | Modern JavaScript and ES6+ | Classes and inheritance | Classes and inheritance |  | 40
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Introduction to React.js | React intro with npm theory about it | 2.2.11 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Introduction to React.js | node setup with jsx | 2.2.12 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Setting Up React Project | Setting up a new React project using Create React App | 2.2.13 | 100
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Components and Props | Understanding functional and class components | 2.2.14 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | State Management | Introduction to useState Hook | 3.1.1 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Event Handling in React | Handling user events (click, input change) | 3.1.2 | 90
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Event Handling in React task | task with handling events with react | 3.1.3 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | dom vs vom | vom structure with react | 3.1.4 | 35
Intermediate | Frontend Development with React | React Js Intermediate to Advance | hooks in react | types of hooks all in vom | 3.1.5 | 90
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Introduction to React Hooks | Understanding hooks: useState, useEffect | 3.1.6 | 90
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Using useEffect Hook | Side effects and fetching data in React | 3.1.7 | 80
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Introduction to React Router | Setting up routes in React | 3.2.1 | 90
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Introduction to React Router | React router task with multiple pages | 3.2.2 | 90
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Working with Route Parameters | Dynamic routing with React Router | 3.2.3 | 90
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Nested Routing in React | Creating nested routes in React | 3.2.4 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | useReducer Hook | Managing complex state using useReducer | 3.2.5 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Global State with Context API | Using Context API to manage global state | 3.2.6 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Global State with Context API | Task on building api weather with react json | 3.3.1 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | React.memo | Optimize functional components with React.memo | 3.3.2 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | useCallback and useMemo | Avoid unnecessary re-renders | 3.3.3 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Creating Custom Hooks | Abstract reusable logic into custom hooks | 3.3.4 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Advanced Form Handling with Formik | Form validation using Formik and Yup | 3.3.5 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Handling Errors Gracefully | Implementing error boundaries in React | 4.1.1 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Lazy Loading Components | Use React.lazy and Suspense to split code | 4.1.2 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | React Build Process | What happens when you run npm run build | 4.1.3 | 50
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Deployment Platforms | Step-by-step deployment of a React app | 4.1.4 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | React Developer Tools | Using React DevTools for debugging | 4.1.5 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | ESLint and Prettier | Code quality and formatting tools | 4.1.6 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Redux Basics | Intro to Redux and store management | 4.1.7 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | Redux Toolkit | Modern Redux with Redux Toolkit | 4.1.8 | 60
Intermediate | Frontend Development with React | React Js Intermediate to Advance | firebase installation | setup firebase with react | 4.1.9 | 100
Intermediate | Frontend Development with React | React Js Intermediate to Advance | firebase auth | firebase auth with react | 4.1.10 | 100
|  | React Js Intermediate to Advance | firebase crud | firebase crud | 4.2.1 | 100
Intermediate | Backend development | Introduction to Node.js | Introduction to Node.js | What is Node.js, Features, Installation, Real-world Use Cases | 4.2.2 | 60
Intermediate | Backend development | Introduction to Node.js | Understanding Node.js Runtime | Node.js Runtime, Asynchronous Nature, Call Stack, Event Loop | 4.2.3 | 60
Intermediate | Backend development | Introduction to Node.js | Node.js Architecture | Event-driven Architecture, V8 Engine, Core Components | 4.2.4 | 60
Intermediate | Backend development | Introduction to Node.js | Event-driven Architecture | EventEmitter, Custom Events, Real-world Scenarios | 4.3.1 | 60
Intermediate | Backend development | Introduction to Node.js | Non-blocking I/O | Blocking vs Non-blocking, Asynchronous APIs, Practical Use | 4.3.2 | 60
Intermediate | Backend development | Introduction to Node.js | Working with File System | fs Module, Reading/Writing, Synchronous vs Asynchronous Handling | 4.3.3 | 60
Intermediate | Backend development | First Node.js Application | Creating a Basic Server | HTTP Module, Hello World, Request-Response Lifecycle | 4.3.4 | 60
Intermediate | Backend development | First Node.js Application | Rendering HTML | Sending HTML, Static Files, Overview of Template Engines | 4.3.5 | 60
Intermediate | Backend development | First Node.js Application | Understanding Modules | require(), exports, Built-in Modules, Caching | 4.4.1 | 70
Intermediate | Backend development | First Node.js Application | HTTP Status Codes | 200, 404, 500, Response Headers, Real-world Cases | 4.4.2 | 70
Intermediate | Backend development | First Node.js Application | Nodemailer + Client Mail | Sending Mail, SMTP Setup, Client Email Handling | 4.4.3 | 60
Intermediate | Backend development | First Node.js Application | File Methods | fs Module Deep Dive, File Operations, Streams | 4.4.4 | 30
Intermediate | Backend development | First Node.js Application | File Paths | path Module, __dirname vs __filename, Absolute vs Relative | 5.1.1 | 30
Intermediate | Backend development | First Node.js Application | npm & Modules | npm init, Local/Global Modules, Semantic Versioning | 5.1.2 | 30
Intermediate | Backend development | First Node.js Application | External Modules | Installing & Using Modules (chalk, axios), Pokémon API Integration | 5.1.3 | 30
Intermediate | Backend development | First Node.js Application | Real-time Modules | WebSockets, Socket.io, Real-time Chat Example | 5.1.4 | 60
Intermediate | Backend development | Express js | Introduction to Express.js | Why Express?, Features, Node.js vs Express | 5.1.5 | 30
Intermediate | Backend development | Express js | Installing Express.js | Project Setup, Folder Structure, Basic App | 5.1.6 | 30
Intermediate | Backend development | Express js | Routing | Static & Dynamic Routes, Route Params, Route Chaining | 5.2.1 | 60
Intermediate | Backend development | Express js | RESTful APIs | CRUD Operations, REST Principles, Best Practices | 5.2.2 | 60
Intermediate | Backend development | Express js | Middleware | Types, Custom Middleware, Execution Flow | 5.2.3 | 60
Intermediate | Backend development | Express js | Templating Engines | EJS Setup, Embedding JS, Loops in EJS | 5.2.4 | 60
Intermediate | Backend development | Express js | Static Files | express.static, Serving Assets (CSS, JS, Images) | 5.2.5 | 60
Intermediate | Backend development | Express js | Error Handling | try-catch, Custom Middleware, Logging Errors | 5.2.6 | 60
Intermediate | Backend development | Express js | Forms and Input | body-parser, Handling POST Data, Validation | 5.2.7 | 60
Intermediate | Backend development | Express js | Express Config | dotenv, Environment Setup, Configuration Patterns | 5.2.8 | 30
Intermediate | Backend development | Express js | Postman Testing | Setting up Postman, Sending GET, POST Requests, Validating Responses | 5.2.9 | 60
Intermediate | Backend development | Express js | Middleware for Logging and Authentication | Custom middleware for logging user actions, user authentication flow | 6.1.1 | 60
Intermediate | Backend development | Express js | RESTful API Best Practices | API versioning, handling status codes, error responses | 6.1.2 | 50
Intermediate | Backend development | Express js | Advanced Middleware Techniques | Rate limiting, request validation, structured error handling | 6.1.3 | 50
Intermediate | Backend development | Express js | Hands-On Advanced API Development | Implement middleware versioning, rate limiting in a RESTful API | 6.1.4 | 60
Intermediate | Backend development | Express js Jwt auth | Intro to JWT | What is JWT, Structure, How it Works | 6.1.5 | 30
Intermediate | Backend development | Express js Jwt auth | Implementing JWT | Token Generation, Verification, Expiry | 6.1.6 | 60
Intermediate | Backend development | Express js Jwt auth | Securing APIs | Middleware for JWT, Protecting Routes, Refresh Tokens | 6.2.1 | 60
Intermediate | Backend development | Express js Jwt auth | Postman Testing for JWT | Testing JWT Authentication in Postman (Token generation and validation) | 6.2.2 | 60
Intermediate | Backend development | Mongodb | Introduction to MongoDB | MongoDB Overview, Features, Cloud Account Setup, MongoDB Atlas, Mongo Shell and Compass Installation | 6.2.3 | 60
Intermediate | Backend development | Mongodb | MongoDB Data Model | Documents & Collections, BSON, Schema-less Design, Embedding vs Referencing Data | 6.2.4 | 60
Intermediate | Backend development | Mongodb | CRUD Operations in MongoDB | insertOne, insertMany, find, updateOne, updateMany, deleteOne, deleteMany, Upserts | 6.2.5 | 60
Intermediate | Backend development | Mongodb | MongoDB Query Language (Shell) | Query Filters, Projections, Sorting, Pagination using skip & limit, Logical Operators | 6.2.6 | 60
Intermediate | Backend development | Mongodb | Indexing in MongoDB | Why Indexes?, Types (Single, Compound, Geospatial), Explain Plans, Performance Optimization | 6.3.1 | 60
Intermediate | Backend development | Mongodb | Aggregation Framework | Aggregation Pipeline, $match, $group, $project, $sort, $lookup (Joins) | 6.3.2 | 60
Intermediate | Backend development | Mongodb | MongoDB Performance Tuning | Query Optimization, Indexes, Query Profiling, Aggregation Pipeline Tips | 6.3.3 | 60
Intermediate | Backend development | Mongodb | MongoDB Drivers | MongoDB Node.js Driver, Connection Setup, Performing Queries using Driver | 6.3.4 | 60
Intermediate | Backend development | Mongodb | Introduction to Mongoose | What is Mongoose?, Advantages of ODM, Creating Schemas and Models, Connecting Mongoose to MongoDB | 6.3.5 | 60
Intermediate | Backend development | Mongodb | Setting Up Mongoose Models | Defining Schemas and Models, Data Types in Mongoose, Integrating Models with Express Routes | 6.3.6 | 60
Intermediate | Backend development | Mongodb | Validating Data in Mongoose | Built-in Validators (required, min, max, enum), Custom Validators, Regex Patterns, Async Validation | 7.1.1 | 60
Intermediate | Backend development | Mongodb | Relationships and Population | One-to-Many, Many-to-Many Relationships, Using populate() for Joins | 7.1.2 | 60
Intermediate | Backend development | Mongodb | Mongoose Middleware | Pre/Post Hooks, Model and Query Middleware, Lifecycle Methods | 7.1.3 | 60
Intermediate | Backend development | Mongodb | Mongoose Query Builder | Creating Advanced Queries using .find(), .aggregate(), and chaining queries | 7.1.4 | 60
Intermediate | Backend development | Rest Api | Authentication and Authorization | Local Strategy, JWT Token-Based Auth, Protecting Routes, Authorization Middleware | 7.1.5 | 60
Intermediate | Backend development | Rest Api | Testing Express.js Applications | Unit Testing APIs using Mocha & Chai, Integration Testing, Mocking DB with Sinon or Mockgoose | 7.2.1 | 60
Intermediate | Backend development | Rest Api | Deployment Strategies | Hosting on Heroku/DigitalOcean/AWS, Environment Variables, MongoDB Atlas Deployment | 7.2.2 | 60
Intermediate | Backend development | Rest Api | Performance Optimization Techniques | MongoDB Indexing, Query Optimization, Node.js Event Loop Performance Tips, Caching | 7.2.3 | 60
Intermediate | Backend development | Rest Api | Postman Testing for Express APIs | Testing REST APIs with Postman, Validating Responses, Automation Scripts | 7.2.4 | 60
Intermediate | Backend development | Rest Api | Introduction to Full CRUD | CRUD in MERN Context, Designing Models & Routes, Planning Endpoints | 7.3.1 | 30
Intermediate | Backend development | Rest Api | Implementing CRUD in MongoDB | Real-time CRUD Example, Writing and Testing Endpoints, Error Handling, Structuring Controllers | 7.3.2 | 60
Intermediate | Backend development | Rest Api | Validating Data in CRUD | Field Validation, Required Fields, Length Constraints, Regex Validation | 7.3.3 | 60
Intermediate | Backend development | Rest Api | CRUD API Error Handling | Handling Validation Errors, Custom Error Messages, Error Codes | 8.1.1 | 60
Intermediate | Backend development | Rest Api | MongoDB Transactions | Using session for Transactions in MongoDB, ACID Properties, Error Recovery | 8.1.2 | 60
Intermediate | Backend development | Rest Api | Introduction to Full CRUD | What is CRUD in Full Stack?, Frontend–Backend–Database Integration Flow, Designing Routes and Models | 8.1.3 | 30
Intermediate | Backend development | Rest Api | Implementing CRUD in MongoDB | End-to-end CRUD App with Express + MongoDB + Mongoose, Controller-Service-Model Structure, Query Optimization for Large Datasets | 8.1.4 | 60
Intermediate | Backend development | Rest Api | API Testing & Debugging | Using Postman for Full CRUD API Testing, Troubleshooting API Responses | 8.1.5 | 60
Intermediate | Backend development | Rest Api | Introduction to Cloud Deployment | Benefits of cloud deployment platforms (Render, Netlify, AWS), overview of cloud platforms | 8.1.6 | 30
Intermediate | Backend development | Rest Api | Environment Variables and Configuration | Using dotenv for environment setup, managing variables for dev vs prod environments | 9.2.1 | 60
Intermediate | Backend development | Rest Api | Building and Bundling Applications | Webpack and Vite bundling, optimizing build processes for React/Node.js apps | 9.2.2 | 60
Intermediate | Backend development | Rest Api | Deploying Frontend to Netlify | Setting up Netlify, React app CLI deployment, connecting with GitHub, configuring environment variables | 9.2.3 | 60
Intermediate | Backend development | Rest Api | Deploying Backend to Render | Setting up Render, deploying Node.js/Express apps, connecting MongoDB, environment variables | 9.2.4 | 60
Intermediate | Backend development | Rest Api | Deploying to AWS EC2 | AWS EC2 basics, instance setup, connecting to the app, SSH access, environment configuration | 9.3.1 | 60
Intermediate | Backend development | Rest Api | Hands-On Frontend Deployment | Deploying a React app to Netlify with environment variables, continuous integration pipeline | 9.3.2 | 60
Intermediate | Backend development | Rest Api | Hands-On Backend Deployment | Deploying Node.js/Express app to Render, connecting MongoDB, setting environment variables | 9.3.3 | 60
Intermediate | Backend development | Rest Api | Introduction to DevOps | What is DevOps? Overview of CI/CD, DevOps tools (Jenkins, GitHub Actions, Docker, Kubernetes) | 10.1.1 | 30
Intermediate | Backend development | Rest Api | CI/CD with GitHub Actions | Setting up GitHub Actions workflows, automated testing, deployment to cloud platforms | 10.1.2 | 60
Intermediate | Backend development | Rest Api | Containerization Basics | Introduction to Docker, containerizing MERN apps, creating Dockerfiles for both frontend & backend | 10.1.3 | 60
Intermediate | Backend development | Rest Api | Monitoring and Logging | Basic monitoring tools (Prometheus, Grafana), logging setup with Winston, error tracking | 10.1.4 | 60
Intermediate | Backend development | Rest Api | Hands-On CI/CD Pipeline | Configuring a GitHub Actions pipeline for automated deployment, integrating tests, environment setup | 10.1.5 | 60
Intermediate | Backend development | Rest Api | Setting up the Backend Server | Introduction to Express.js and Node.js, Setting up Express server, Middleware configuration | 10.1.6 | 60
Intermediate | Backend development | Rest Api | Connecting React with Express | Using Axios or Fetch to connect frontend with backend, API endpoint calls | 11.1.1 | 35
Intermediate | Backend development | Rest Api | Data Flow between Frontend and Backend | Understanding REST API calls in React, Handling responses in React | 11.1.2 | 60
Intermediate | Backend development | Project | Project Setup | Setting up both React and Express in a single project folder, Directory structure | 11.1.3 | 40
Intermediate | Backend development | Project | Full-Stack CRUD App | Implementing full CRUD operations with MongoDB, Express.js, React, and Node.js | 12.1.1 | 50
Intermediate | Backend development | Project | Authentication and Authorization | Implementing JWT authentication in the MERN stack, Secure routes and user sessions | 12.1.2 | 60
9635